## Slide 1
April 5, 2012
Managing Mine Slimes and Other Lessons Learned
Jack Waite Mine Removal Action
Todd Bragdon, CDM Smith
Brandon Ball, Parametrix
Bill Adams, EPA Region 10
Rod Zion, USACE Seattle
Jeff Johnson, US BLM
Rich Hamlin, Conti

## Slide 2: Introduction
Project Team
  Parametrix / CDM Smith; Engineering Design
  U.S. EPA Region 10; Lead Regulatory Agency
  U.S. Forest Service; Property Owner, Joint Lead Regulatory Agency
  U.S. Army Corps of Engineers – Seattle District; Construction Procurement and Administration
  Conti; Removal Action Contractor
Site Features and 2011-2012 Removal Actions
  Removal of two tailings piles (TP1 and TP2) and Mill area in alluvial valley
  Consolidation to two repositories: TP3 and Borrow Area 2 (BA2)
  Rehabilitation of Tributary Creek
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 3: Jack Waite Mine Layout
Managing Mine Slimes – Jack Waite Mine Removal Action
N
Tailings Pile TP3
Borrow Area 1
Borrow Area 2
Tailings Pile TP2
Tailings Pile TP1
1500-Level Adit
and Waste Rock Pile
Tailings Pile TP4

## Slide 4: Tailings Pile 1, Mill Area, & Tributary Creek
Managing Mine Slimes – Jack Waite Mine Removal Action
TP-1 (110,000 cy); Mill Area (14,000 cy); Alluvium (2,900 cy)
TP1
Mill
Tributary Creek

## Slide 5: Tailings Pile 2
Managing Mine Slimes – Jack Waite Mine Removal Action
TP-2 (15,000 cy Tailings)
TP2

## Slide 6: Materials Management & Restoration (MMR) Issues
2011 MMR Issues Encountered at the Jack Waite Site
  Difficult material types
  Additional waste volumes
  Insufficient borrow soil gradation characterization
  TP3 alluvial repository configuration
  Remote high elevation site; limited construction season
Issue Discussion
  Design approach
  2011 construction issue
  Solutions / lessons learned
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 7: Difficult Material Types
Design Approach
  Borings and cone penetrometers completed through tailings piles
2011 Construction Issue
  TP2 slimes encountered in July 2011
  Difficult to excavate material
  Difficult to haul material – transportation caused separation of solids / liquids & spills
Solutions / Lessons Learned
  Temporary stockpile material to dewater, addition of Portland Cement (5%); transportable; achieved good compaction
  For tailings piles, focus on potential volume of this material
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 8: Additional Waste Volumes
Design Approach
  Aerial survey / LiDAR data (2-ft. topographic contouring)
  Test pit and boring extent / depth of mine wastes
  Mine waste volumetrics developed using CAD 3D
  Contingency volumes included (~30 Percent)
2011 Construction Issue
  Additional waste rock volume at Mill Site (34,000 vs. 14,000 cy)
  Additional tailings volume at TP2 (23,000 vs. 15,000 cy)
  2012 concerns with waste volume in Tributary Creek alluvium
Solutions / Lessons Learned
  Flexibility in repository design to allow additional capacity
  Steep slopes and alluvial interface difficult to estimate
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 9: Insufficient Borrow Soil Gradation Characterization
Design Approach
  Repository cover / rehabilitation area growth media and fill primarily developed from Borrow Area 2
  Test pits used to estimate depth of borrow soils
  Field observations / geotechnical data used to evaluate gradation (oversize vs. granular material)
  Borrow soil volumetrics developed using CAD 3D and gradation
2011 Construction Issue
  Significantly more oversize material - 19,000 cy vs. 11,000 cy
  Limited stockpiling areas / double handling in steep terrain
Solutions / Lessons Learned
  Design approach should use grizzly / screening for oversize rock
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 10: TP3 Alluvial Repository Configuration
Design Approach
  EE/CA and Action Memorandum included TP2 repository located in Tributary Creek alluvial valley
  Volume and cost constraints
  Maximize mine waste in BA2 repository
  Utilize low permeability cover to reduce infiltration
  Utilize riprap toe armoring (100-yr event) ; HEC-RAS model
2011 Construction Issue
  Tailings piping observed
Solutions / Lessons Learned
  Revised design to include toe drain system
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 11: Remote High Elevation Site
Design Approach
  Completed design / contracting process in 2010 (utilized $1.2M ARAR funding)
  Allowed for snow removal in bid for early mobilization
  Allowed for flexibility in bid for one or two-season construction
2011 Construction Issue
  Snow plowed in May; heavy precipitation in June; limited site construction until July
Solutions / Lessons Learned
  Field conditions can significantly impact schedule
  Consider summer traffic on hauling
Managing Mine Slimes – Jack Waite Mine Removal Action

## Slide 12: Questions
Managing Mine Slimes – Jack Waite Mine Removal Action